## Planning du Cours
| Lieu | Intervenant | DATE | Horaire début | Horaire Fin | Cours
1 | Polytech | J.-Y. Tigli | 2017-09-20 | 9:00 | 12:15 | Introduction aux spécificités de la conception et le développement sur terminaux mobiles
2 | Polytech | J.-Y. Tigli | 2017-09-27 | 8:00 | 12:15 | Les différents niveaux de développement - premier niveau Web et Web Responsive Design CSS3/HTML5
3 | Polytech | C. Dartigues | 2017-10-04 | 8:00 | 12:15 | Projet : Introduction au marchine learning : algorithmes de classification et de reconnaissance
4 | Polytech | J.-Y. Tigli | 2017-10-11 | 8:00 | 12:15 | Les différents niveaux de développement - Développement Cross-Plateformes. Ex. Xamarin
5 | Polytech | G. Marro | 2017-10-18 | 8:00 | 12:15 | Patterns Logiciels associés au développement sur terminaux mobiles - Diffusion des applications mobiles et App Stores
6 | Polytech | G. Marro | 2017-10-25 | 8:00 | 12:15 | Développement Natif : Introduction Android
7 | Polytech | G. Marro | 2017-11-08 | 8:00 | 12:15 | Développement Natif : Android et les différentes API Graphiques pour cibles hétérogènes telles que les Mobiles, les montres, les Android TV.
8 | Polytech | G. Marro | 2017-11-15 | 8:00 | 12:15 | Développement Natif : SDK et accès aux capteurs/actionneurs sur les cibles Android
9 | Polytech | J.-Y. Tigli, G. Marro | 2017-12-20 | 8:00 | 12:15 | Jalon 1 de Projet - Audit intermédiaire de Projet
10 | Polytech | N. Ferry | 2018-01-10 | 8:00 | 12:15 | Développement Natif : Accès Web Service (accès synchrone / asynchrone) sous Android
11 | Polytech | G. Marro | 2018-01-17 | 8:00 | 12:15 | Développement Natif : Autres Tutoriaux Android
12 | Polytech | G. Marro | 2018-01-24 | 8:00 | 12:15 | Développement Natif : Cours et Démonstration de l'environnement de dev Apple : Xcode / Objective C / Swift
13 | Polytech | G. Marro | 2018-01-31 | 8:00 | 12:15 | Développement Natif : Programmation iOS, prise en main de XCode, applications utilisant les Segues, Actions et Outlet
14 | Polytech | G. Marro | 2018-02-07 | 8:00 | 12:15 | Développement Natif : programmation Swift, accès capteurs/actionneurs, création de listes
15 | Polytech | G. Rey (J.-Y. Tigli) | 2018-02-14 | 8:00 | 12:15 | Futur des terminaux mobiles : Werable Computers - Test Hololens de Microsoft
16 | Polytech | J.-Y. Tigli & G. Marro | 2018-02-21 | 8:00 | 12:15 | Jalon 2 de Projet : Audit final de Projet
Note on A1: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on C1: Task Lead Enter the name of the Task Lead in this column.
Note on D1: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G1: Task Enter the name of each task and sub-task. Use indents for sub-tasks.

## Suivi de Projet par Etudiants
Module ELIM 2017 2018
Polytech Nice Dep SI -SI5 - IHM
| Project Start Date: |  |  | 2017-09-20 | time axis 2017-09-18 to 2018-03-04
| Afficher Semaine |  |  | 1 |  |  |  |  | 2017-09-18: Week 1; 2017-09-25: Week 2; 2017-10-02: Week 3; 2017-10-09: Week 4; 2017-10-16: Week 5; 2017-10-23: Week 6; 2017-10-30: Week 7; 2017-11-06: Week 8; 2017-11-13: Week 9; 2017-11-20: Week 10; 2017-11-27: Week 11; 2017-12-04: Week 12; 2017-12-11: Week 13; 2017-12-18: Week 14; 2017-12-25: Week 15; 2018-01-01: Week 16; 2018-01-08: Week 17; 2018-01-15: Week 18; 2018-01-22: Week 19; 2018-01-29: Week 20; 2018-02-05: Week 21; 2018-02-12: Week 22; 2018-02-19: Week 23; 2018-02-26: Week 24
| PLANNING DU PROJET ELIM | [7 empty] | 2017-09-18: 2017-09-18; 2017-09-25: 2017-09-25; 2017-10-02: 2017-10-02; 2017-10-09: 2017-10-09; 2017-10-16: 2017-10-16; 2017-10-23: 2017-10-23; 2017-10-30: 2017-10-30; 2017-11-06: 2017-11-06; 2017-11-13: 2017-11-13; 2017-11-20: 2017-11-20; 2017-11-27: 2017-11-27; 2017-12-04: 2017-12-04; 2017-12-11: 2017-12-11; 2017-12-18: 2017-12-18; 2017-12-25: 2017-12-25; 2018-01-01: 2018-01-01; 2018-01-08: 2018-01-08; 2018-01-15: 2018-01-15; 2018-01-22: 2018-01-22; 2018-01-29: 2018-01-29; 2018-02-05: 2018-02-06; 2018-02-12: 2018-02-13; 2018-02-19: 2018-02-20; 2018-02-26: 2018-02-27
1 | Planning de Projet de module | Groupe d'Etudiants | "Backlog" / URL | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1.1 | Sprint 1 | GR3 | https://github.com/dl100463/Sms-Analysis-App/blob/master/Backlogs/Log1.txt | 2017-09-27 | 2017-10-25 | 29 | 100% | 21 | bar: 2017-09-25 W to 2017-10-23 W
1.2 | Sprint 2 | GR3 | https://github.com/dl100463/Sms-Analysis-App/blob/master/Backlogs/Log2.txt | 2017-10-25 | 2017-11-08 | 15 | 100% | 11 | bar: 2017-10-23 W to 2017-11-06 W
1.3 | Sprint 3 | GR3 | https://github.com/dl100463/Sms-Analysis-App/blob/master/Backlogs/Log3.txt | 2017-11-08 | 2017-11-22 | 15 | 100% | 11 | bar: 2017-11-06 W to 2017-11-20 W
1.4 | Sprint 4 | GR3 | https://github.com/dl100463/Sms-Analysis-App/blob/master/Backlogs/Log4.txt | 2017-12-18 | 2017-12-25 | 8 | 3770312% | 6 | bar: 2017-12-18 M to 2017-12-25 M
1.5 | Sprint 5 | GR3 | https://github.com/dl100463/Sms-Analysis-App/blob/master/Backlogs/Log5.txt | 2018-01-10 | 2018-01-17 | 8 | 0% | 6 | bar: 2018-01-08 W to 2018-01-15 W
1.6 | Sprint 6 | GR3 | https://github.com/dl100463/Sms-Analysis-App/blob/master/Backlogs/Log6.txt | 2018-01-17 | 2018-01-24 | 8 | 0% | 6 | bar: 2018-01-15 W to 2018-01-22 W
1.7 | Sprint 7 | GR3 | https://github.com/dl100463/Sms-Analysis-App/blob/master/Backlogs/Log7.txt | 2018-01-24 | 2018-01-31 | 8 | 0% | 6 | bar: 2018-01-22 W to 2018-01-29 W
1.8 | Sprint 8 | GR3 | https://github.com/dl100463/Sms-Analysis-App/blob/master/Backlogs/Log8.txt | 2018-01-31 | 2018-02-07 | 8 | 0% | 6 | bar: 2018-01-29 W to 2018-02-06 W
1.9 | Sprint 9 | GR3 | https://github.com/dl100463/Sms-Analysis-App/blob/master/Backlogs/Log9.txt | 2018-02-07 | 2018-02-14 | 8 | 0% | 6 | bar: 2018-02-06 W to 2018-02-13 W
1.10 | Sprint 10 | GR3 | https://github.com/dl100463/Sms-Analysis-App/blob/master/Backlogs/Log10.txt | 2018-02-14 | 2018-02-21 | 8 | 0% | 6 | bar: 2018-02-13 W to 2018-02-20 W
2 | JALONS | Groupe d'Etudiants
2.1 | Prototype 1 | GR3 |  | 2017-12-20 | 2017-12-20 | 1 | 0% | 1 | bar: 2017-12-18 W
2.2 | Prototype Final | GR3 |  | 2018-02-21 | 2018-02-21 | 1 | 0% | 1 | bar: 2018-02-20 W
Note on F8: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on H8: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I8: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on J8: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.